## Instructions
Instructions
Note 1 | There is a limit of 12 weeks for the length of a sprint in this tool.
Note 2 | The burn down chart was created with the assumption that you will have a scrum meeting at the beginning of day 1. So, no story points will be completed.
Note 3 | Data fields are yellow. Only change the data fields on the spreadsheet, and the chart reference column number per the instructions below.
Note 4 | It is assumed you will use and save a file for each sprint.
On the "Control Data" Tab
Step 1 | Assign the number of weeks for each sprint. There is a 12 week limit on this tool. You will reeive an Over Limit message if you exceed this limit (field C2).
Step 2 | Assign the number of team members on your scrum team (field C3).
Step 3 | Assign the number of story points each team member will consume each week. As suggested in Chapter 21, this will be the amount of work in hours per week (field C4).
Step 4 | Optional: If the capacity per week does not match your team's agreed to method of allocation, you can override the calculated capacity per week (field C6). If you don't use this field, leave it blank.
Before your Sprint starts, Change the following on the "Worksheet" tab
Step 5 | Make note of what column label your data ends in, and then right-click on the middle of the chart, and then click on Select Data.
Step 6 | In the Select Data Source dialog box, under Horizontal (Category) Axis Labels, click Edit. In the Axis Labels dialog box, modify the Axis label range so the last letter matches the column you noted in the previous step. You must keep the the dollar sign symbols ($) on each side of the column lablel. Click OK when finished to return to the Select Data Source dialog box.
Step 7 | In the Select Data Source dialog box, under Legend Entries (Series), select Expected Burn-Down, and then click Edit. In the Edit Series dialog box, modify the Series name so the last letter matches the column you noted in step 5. You must keep the the dollar sign symbols ($) on each side of the column lablel. Click OK when finished to return to the Select Data Source dialog box.
Step 8 | In the Select Data Source dialog box, under Legend Entries (Series), select Actual Burn-Down and then click Edit. In the Edit Series dialog box, modify the Series values so the last letter mathes the column you noted in step 5. You must keep the the dollar sign symbols ($) on each side of the column lablel. Click OK when finished to return to the Select Data Source dialog box and then click OK.
During the Sprints
Step 9 | Follow the directions in Chapter 21, "Record progress from daily scrum metings," to configure the percent complete for board status items. On day one there will be no change except for moving stories planned for that day from Not Started to Next Up. It is assumed that you will use 0%, 0%, 50%, and 100% in each of your four status buckets.
Step 10 | On day two, at the start of your sprint, adjust the Current Sprint Board. Then go to the Current Sprint Sheet. Copy the Work column for that day from Microsoft Project and paste it into the correct day in rows 33 - 102 on the Worksheet tab in Excel. When you copy from Microsoft Project the field name will come with the data, so make sure to paste starting in row 33 (titled work), in the correct column, for the current day. On the Hone tab, in the Editing group, in the Find & Select list, click Replace. In the Find and Replace dialog box, in the Find what box, type hrs, leave the Replace with box blank and then click Replace All. When prompted click OK, and then Close to finish the replacements and update the chart. Note: The Worksheet tab has been set up to begin on day two to align with these instructions.
Step 11 | Repeat each day. The burn down chart will adjust daily based on your progress.

## Control Data
Time of each sprint | 4 | weeks
Number of people on the scrum team | 8
Story points available per team member per week | 30
Capacity per week | 240
Override capacity per week (exceptions) |  | (Optional)
960
0

## Worksheet
8
960
50.5263
20
Day of SPRINT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Expected Burn-Down | 960 | 909.4737 | 858.9474 | 808.4211 | 757.8947 | 707.3684 | 656.8421 | 606.3158 | 555.7895 | 505.2632 | 454.7368 | 404.2105 | 353.6842 | 303.1579 | 252.6316 | 202.1053 | 151.5789 | 101.0526 | 50.5263 | 2.1316e-13
Actual Burn-Down | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960 | 960
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work | work